## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
u1 | Creating account A | As a user of the bank system, I want to create my own account , so that I can select the most appropriate service. | 1 | 1 | 1.The interface offers the choices of three types of accouny for users. |  | 4.01 | 4.14
u3 | Creating account B | As a user of the bank system, I want to be assigend with the specific account number, so that I can be identified by the system. | 2 | 2 | 1.The account number will be set by radom. Each account number will be used to create a txt file. | The filename of the particular txt is an account number, it is not possible that two people have the same account number. | 4.01 | 4.14
u2 | Login pin | As a user of the bank system, I want to get a unique initial pin when I create an account. So that I can use this pin to login. | 2 | 2 | 1.The user will be assigned a 6 bit pin when creating account. | The pin is a random value. | 4.15 | 4.28
u4 | Saver account withdraw | As a householder who want to save money, I hope that I can only withdraw funds from my account if the funds don't exceed the balance and I have reserved several days ago. So that I can save money and control the cost of my family. | 2 | 2 | 1.Make sure that funds are withdrawn from the account matches the account that customer have already offered. 2.Make sure that the balance in the particular txt file wil change after this operation. 3.People only can withdraw money from saver account after 30 days after they deposit money. 4.People only can withdraw money don't exceed the balance | 1.This operation will finish only if the status of the account is active. 2.The current time will compare to the last time the user deposited fund. | 4.15 | 4.28
u5 | Junior account withdraw | As a junior user of the bank system, I hope that I can only withdraw funds from my account if the funds don't exceed the balance. So that I won't owe money which I don't have the ability to pay back. | 2 | 2 | 1.Make sure that funds are withdrawn from the account matches the account that customer have already offered. 2.Make sure that the balance in the particular txt file wil change after this operation. 3.People only can withdraw money don't exceed the balance | This operation will finish only if the status of the account is active. | 4.15 | 4.28
u6 | Current account withdraw | As an adult who has ability to pay the debt, I hope that I can withdraw funds from my account if the funds don't exceed the limit. So that I can buy things I like even if I don't have enough money. | 2 | 2 | 1.Make sure that funds are withdrawn from the account matches the account that customer have already offered. 2.Make sure that the balance in the particular txt file wil change after this operation. 3.People only can overdraft money don't exceed the overdraft limit (500 dollars) | This operation will finish only if the status of the account is active. | 4.15 | 4.28
u7 | Deposit fund(1) | As a user of the bank system, I want to login in my account and deposit funds to the account I want to deposit to. So that I can deposit money to myself or others. | 1 | 2 | 1.Make sure that funds are deposited to the account matches the account that customer have offered. 2.Make sure that the balance in the particular txt file wil change after this operation. 3.People will be required to enter an account number which they want to deposit money to | 1.This operation will finish only if the status of the account is active. 2.The time when deposit fund will be recorded. | 4.15 | 4.28
u8 | Deposit fund(2) | As a user of the bank system, I want to deposit money by cash or by check. So that I can deposit money if I don't carry cash on me. | 2 | 3 | 1.People will be required to enter the way to deposit money(By cash or by cheque) 2.If by cash, the balance of account will change immediately. 3.If by cheque, the amount of money will be restored in unclear money in the file. | This operation will finish only if the status of the account is active. | 4.29 | 5.12
u9 | Suspend account | As a user of the bank system, I want to suspend my account in case of occuring of some situations. So that the status of my account will be inactive and no operations can be done. | 2 | 2 | 1.People can choose "suspend account" after login to suspend this account. 2.The status stored in txt file will change (boolean value will change to "False") after this operation. | The user will be required to input his pin again to confirm his operation. | 4.15 | 4.28
u10 | Recover account | As a user of the bank system, I want to recover the status of my account. So that my account bacome active again and further transactions can be done. | 2 | 2 | 1.People can choose "recover account" after login to recover this account and make it active again. 2.The status stored in txt file will change (boolean value will change to "True") after this operation. | The user will be required to input his pin again to confirm his operation. | 4.15 | 4.28
u11 | Close account | As a user of the bank system, I want to close my account if I don't want to use it. So that my account will be closed and the information of me will be deleted. | 3 | 3 | 1.People can choose "Close account" after login to close account and clear information (txt file will be deleted) | The user will be required to input his pin again to confirm his operation. | 4.29 | 5.12
u12 | Check the balance and unclear money | As a user of the bank system, I want to be able to look up for the balance and unclear money after login. So that I can be aware of the status of my account. | 2 | 3 | 1.Users can choose"check balance" after login. | Balance, unclear money and status of account will be shown. | 4.29 | 5.12
b1 | Show information | As a bank manager, I want the users to enter their basic information such as name, birthday and address to open an account. So that the bank can get information of customers and provide better service. | 1 | 1 | 1.Users are required to provide name, address, birthday, the account type they want to open, pin to open an account. These information will be restored in a txt file. | The user should enter account number to confirm operation. | 4.01 | 4.14
b2 | Credit check | As a bank manager, I hope that there will be a credit check before an account is created. So that people who don't have a satisfactory history credit can't open an account. | 2 | 4 | 1.When the user provides his name, the system will check whether the name is on the bad credit list. 2.If the name is on the list, this user will not be able to create an account. | There will be a txt file named "check.txt", which contains people who don't have a satisfactory history credit. | 5.13 | 5.26
b5 | Clear funds | As a bank manager, I hope that uncleared fund can be cleared by the employees of bank. So that the funds can be cleared after the bank has make sure the authenticity of the cheque. | 2 | 4 | 1.After entering the administrator page, employee can choose to clear the unclear funds of a particular customer by entering his account number. | Then the unclear fund will be added on the balance. And the unclear fund will be 0. | 5.13 | 5.26